## Individual and Team Missions
Name:
Individual Missions (To be reported through this excel sheet)
| Date Fulfilled | Proof (e.g. Link, Text, …)
Add a new story with acceptance criteria, fulfilling the definition of ready.
Finish an feature story, fulfilling the definition of done.
Commit + Push a change to the production version.
Hold a retrospective for the team. Take notes.
Participate in a round of planning poker.
Collect product feedback from one person outside the group. Take notes.
Present the current state in a sprint review.
Fill the scrum master role as a servant leader for a week. Take notes on what you did for your team.
Adjust the productive version of the team pitch.
Add new information to the team's hypothesis.
Pitch the current state to Henning Femmer.
Create an automated test case.
Team Missions (To be evaluated at the end of the semester)
Self-organize your team.
Help others to learn about agile.
Help others to fulfill their individual missions.
Validate your assumptions about your product rapidly and adjust your product idea.
Deliver value through an MVP early.

## Jennifer Netzler
Name:
Individual Missions (To be reported through this excel sheet)
| Date Fulfilled | Proof (e.g. Link, Text, …)
Add a new story with acceptance criteria, fulfilling the definition of ready. | 2021-10-25 | siehe Excel "Definition of Ready"
Finish an feature story, fulfilling the definition of done.
Commit + Push a change to the production version.
Hold a retrospective for the team. Take notes.
Participate in a round of planning poker. | 2021-11-08 | siehe Issues
Collect product feedback from one person outside the group. Take notes.
Present the current state in a sprint review.
Fill the scrum master role as a servant leader for a week. Take notes on what you did for your team.
Adjust the productive version of the team pitch.
Add new information to the team's hypothesis. | 2021-11-15 | https://github.com/Dozentenampel/dozentenampel.github.io/issues/5
Pitch the current state to Henning Femmer. | 2021-11-15 | Herr Femmer war da.
Create an automated test case.
Team Missions (To be evaluated at the end of the semester)
Self-organize your team.
Help others to learn about agile.
Help others to fulfill their individual missions.
Validate your assumptions about your product rapidly and adjust your product idea.
Deliver value through an MVP early.

## Susanna Hesse
Name:
Individual Missions (To be reported through this excel sheet)
| Date Fulfilled | Proof (e.g. Link, Text, …)
Add a new story with acceptance criteria, fulfilling the definition of ready. | 2021-10-25 | siehe Excel "Definition of Ready"
Finish an feature story, fulfilling the definition of done. | 2021-11-02 | siehe Excel "Definition of Done"
Commit + Push a change to the production version. | 2021-10-25 | https://github.com/Dozentenampel/dozentenampel.github.io/blob/main/ampelmvp.html
Hold a retrospective for the team. Take notes.
Participate in a round of planning poker. | 2021-11-08 | siehe Issues
Collect product feedback from one person outside the group. Take notes. | 2021-11-07 | Ergebnis: Idee ist gut, Aufbau ist gut, vorallem die alphabetische Reihenfolge und die direkte Sichtbarkeit durch Farben/Punkte
Present the current state in a sprint review.
Fill the scrum master role as a servant leader for a week. Take notes on what you did for your team. | 2021-11-15 | Ausfüllen Mission Report, Studenten für die Präsentation suchen, bie Rückfragen zu Verfügung stehen
Adjust the productive version of the team pitch. | 2021-11-02 | Anpassung des MVP durch Erweiterung der Tabelle mit Informationen zu den Professoren.
Add new information to the team's hypothesis.
Pitch the current state to Henning Femmer. | 2021-10-25 | Herr Femmer war da
Create an automated test case.
Team Missions (To be evaluated at the end of the semester)
Self-organize your team.
Help others to learn about agile.
Help others to fulfill their individual missions.
Validate your assumptions about your product rapidly and adjust your product idea.
Deliver value through an MVP early.

## Kai Pütter
Name:
Individual Missions (To be reported through this excel sheet)
| Date Fulfilled | Proof (e.g. Link, Text, …)
Add a new story with acceptance criteria, fulfilling the definition of ready. | 2021-10-25 | siehe Excel "Definition of Ready"
Finish an feature story, fulfilling the definition of done. | 2021-10-25 | siehe Excel "Definition of Done"
Commit + Push a change to the production version. | 2021-11-08 | https://github.com/Dozentenampel/dozentenampel.github.io/blob/main/ampelmvp.html
Hold a retrospective for the team. Take notes.
Participate in a round of planning poker. | 2021-11-08 | siehe Issues
Collect product feedback from one person outside the group. Take notes.
Present the current state in a sprint review.
Fill the scrum master role as a servant leader for a week. Take notes on what you did for your team. | 2021-10-25 | Fenster öffnen, helfen bei Systemproblemen, Mission Report ausfüllen, Moderation
Adjust the productive version of the team pitch.
Add new information to the team's hypothesis.
Pitch the current state to Henning Femmer.
Create an automated test case.
Team Missions (To be evaluated at the end of the semester)
Self-organize your team.
Help others to learn about agile.
Help others to fulfill their individual missions.
Validate your assumptions about your product rapidly and adjust your product idea.
Deliver value through an MVP early.

## Florian Heiser
Name:
Individual Missions (To be reported through this excel sheet)
| Date Fulfilled | Proof (e.g. Link, Text, …)
Add a new story with acceptance criteria, fulfilling the definition of ready. | 2021-10-25 | siehe Excel "Definition of Ready"
Finish an feature story, fulfilling the definition of done. | 2021-10-25 | siehe Excel "Definition of Done"
Commit + Push a change to the production version.
Hold a retrospective for the team. Take notes.
Participate in a round of planning poker. | 2021-11-08 | siehe Issues
Collect product feedback from one person outside the group. Take notes.
Present the current state in a sprint review.
Fill the scrum master role as a servant leader for a week. Take notes on what you did for your team. | 2021-11-08 | Ausfüllen des Mission Report, Sonnenblende heruntergelassen, Moderation
Adjust the productive version of the team pitch.
Add new information to the team's hypothesis. | 2021-11-08 | https://github.com/Dozentenampel/dozentenampel.github.io/issues/5
Pitch the current state to Henning Femmer. | 2021-11-08 | Herr Femmer war da
Create an automated test case.
Team Missions (To be evaluated at the end of the semester)
Self-organize your team.
Help others to learn about agile.
Help others to fulfill their individual missions.
Validate your assumptions about your product rapidly and adjust your product idea.
Deliver value through an MVP early.